## Sheet1
Project Plan – Team Epsilon
2017-02-03
		February				March				April
	Description	5	12	19	26	5	12	19	26	3	10	17	24
	Milestone I: Overworld
	Character Movement
	NPC interaction
	Combat Hooks
	Menu UI Systems

	Milestone II: Combat System
	Deck Randomization
	Turn Based System
	Combat Animations
	End of combat (apply damage)

	Milestone III: Alpha
	Integrate Overworld and combat
	Story flushed out
	A working location

	Milestone IV: Beta
	All regions of world
	Asset Integration
	Pool of approximately 30 cards per character
	30 non-character specific cards
	Minimum of 4 elemental status types

	Milestone V: Final
	Bug fixes
	Stretch goals